## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Fabienne &Tata | 23/03/2023 | 24/03/2023 | 3 hours | 3 hours
creat and finalize the git repo | Fabienne &Tata | 23/03/2024 | 24/03/2024 | 1 hour | 30 min
Link the database to GIT | Fabienne &Tata | 23/03/2025 | 24/03/2025 | 2 hour | 3 hours
Link the database to colab | Fabienne &Tata | 23/03/2026 | 24/03/2026 | 2 hours | 3 hours
Staging of dimension <name> | Wilfried SANKARA | 18/03/2023 | 18/03/2023 | 1 hour | 1 hour
Staging of dimension <name> | Wilfried SANKARA | 18/03/2023 | 18/03/2023 | 1 hour | 1 hour
…
Surrogate key pipeline | Wilfried SANKARA | 18/03/2023 | 20/03/2023 | 2 hours | 2 hours
Staging of fact table – including FKs and measures | Wilfried SANKARA | 18/03/2023 | 20/03/2023 | 1 hour | 1 hour
Data quality handling and reporting | Wilfried SANKARA | 18/03/2023 | 20/03/2023 | 3 hours | 2h30